## Ark1
ID | Task Name | Assigned | Estimated Time. | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
|  |  |  | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su
1 | Meeting With Client | Everyone | Hours | bar: Week 1 M; Week 2 M; Week 3 M; Week 4 M; Week 4 F
2 | Buy Domain and setupt FTP Accounts | Tobias. Tom | day | bar: Week 1 M to Week 1 T
3 | Create the Homepage | Davis. Tobias. Tom | Week | bar: Week 1 T to Week 1 Su
4 | Create the About page | Davis. Tobias. Tom | Week | bar: Week 2 M to Week 2 Su
5 | Create the Contact page | Davis. Tobias. Tom | Week | bar: Week 3 M to Week 3 Su
6 | Create The content page | Davis. Tobias. Tom | Week | bar: Week 4 M to Week 4 F
7 | Create a movie about production of juice | Adam. Linda | Weeks | bar: Week 1 T to Week 1 F; Week 2 M to Week 2 F; Week 3 M to Week 3 F; Week 4 M to Week 4 T
8 | Upload the video | Adam. Tom. Linda | days | bar: Week 4 W to Week 4 Th
9 | Take Pictures for the website and advertisement | Adam. | Week | bar: Week 1 Th to Week 1 F; Week 2 Th to Week 2 F; Week 3 Th to Week 3 F; Week 4 T
10 | Create a Wepage to show stores that sell the juice | Davis. Linda | Days | bar: Week 3 M to Week 3 T
11 | Add prices from the stores/Add a link to pricing apps | Tobias.Linda | Days | bar: Week 3 W to Week 3 Th